## Task Matrix
Task ID | Phase | Task Name | Description | Pkg A | Pkg B | Pkg C | Pkg D | Automation Target | App Required | Time (min) | Frequency
T001 | Initiation | Receive new client notification | Alert PM of new client assignment | Y | Y | Y | Y | 95% | Task Queue Manager | 5 | Per client
T002 | Initiation | Review client submission | Analyze project type, budget, timeline from intake | Y | Y | Y | Y | 80% | AI Classification | 15 | Per client
T003 | Initiation | Initial phone consultation | Conduct discovery call with client | Y | Y | Y | Y | 0% | Calendar + Script | 45 | Per client
T004 | Initiation | Complete intake form | Document all project requirements | Y | Y | Y | Y | 60% | Smart Forms | 30 | Per client
T005 | Initiation | Upload client documents | Store contracts, photos, plans in vault | Y | Y | Y | Y | 90% | Document Vault | 10 | Per client
T006 | Initiation | Classify project type | Categorize by complexity and requirements | Y | Y | Y | Y | 95% | AI Classification | 5 | Per client
T007 | Initiation | Generate initial estimate | Create budget range estimate | Y | Y | Y | Y | 85% | Estimation Engine | 20 | Per client
T008 | Initiation | Send confirmation email | Welcome email with next steps | Y | Y | Y | Y | 100% | Email Engine | 5 | Per client
T009 | Initiation | Schedule site visit | Book discovery site assessment | N | Y | Y | Y | 90% | Site Visit Scheduler | 10 | Per client
T010 | Initiation | Prepare site assessment checklist | Generate phase-appropriate checklist | N | Y | Y | Y | 95% | Checklist Generator | 5 | Per visit
T011 | Initiation | Conduct site assessment | On-site measurements and documentation | N | N | Y | Y | 0% | Mobile App | 120 | Per visit
T012 | Initiation | Document site photos | Photograph all relevant areas (20+ photos) | N | N | Y | Y | 80% | Photo Documentation | 30 | Per visit
T013 | Initiation | Complete site assessment form | Record all findings and measurements | N | N | Y | Y | 70% | Mobile Assessment | 45 | Per visit
T014 | Initiation | Generate site assessment report | Create formatted report from data | N | N | Y | Y | 95% | Report Generator | 30 | Per visit
T015 | Initiation | Send assessment summary to client | Email report with findings | N | N | Y | Y | 100% | Email Engine | 5 | Per visit
T016 | Initiation | Create project record | Initialize project in system | Y | Y | Y | Y | 100% | API/Database | 5 | Per client
T017 | Initiation | Assign project team | Designate PM and support resources | N | N | N | Y | 80% | Resource Manager | 15 | Per client
T018 | Initiation | Conduct VIP strategy session | Deep-dive planning for enterprise clients | N | N | N | Y | 0% | Calendar | 90 | Per client
T019 | Planning | Determine design requirements | Assess need for architect/designer | Y | Y | Y | Y | 90% | Requirements Engine | 15 | Per project
T020 | Planning | Match with design professional | Source qualified architect/designer | N | N | Y | Y | 85% | Architect Marketplace | 30 | Per project
T021 | Planning | Facilitate design kickoff | Coordinate introductory meeting | N | N | Y | Y | 70% | Calendar + Video | 60 | Per project
T022 | Planning | Review conceptual designs | Evaluate 2-3 design options | N | Y | Y | Y | 40% | Design Review Tool | 60 | Per project
T023 | Planning | Document client selections | Record design preferences and decisions | N | Y | Y | Y | 80% | Decision Log | 20 | Per project
T024 | Planning | Coordinate design development | Manage DD phase with designer | N | N | Y | Y | 60% | Design Tracking | 120 | Per project
T025 | Planning | Review for code compliance | Check drawings against building codes | N | N | Y | Y | 70% | Compliance Checker | 45 | Per project
T026 | Planning | Coordinate engineering | Manage structural/MEP engineering | N | N | Y | Y | 50% | Engineer Network | 90 | Per project
T027 | Planning | Facilitate design approval | Get client sign-off on final design | N | Y | Y | Y | 80% | Approval Workflow | 30 | Per project
T028 | Planning | Obtain construction documents | Secure permit-ready drawings | N | N | Y | Y | 90% | Document Vault | 15 | Per project
T029 | Planning | Identify required permits | Determine permits by jurisdiction | N | Y | Y | Y | 95% | Permit Tracker | 15 | Per project
T030 | Planning | Compile permit package | Assemble application documents | N | N | Y | Y | 80% | Permit Package Builder | 60 | Per permit
T031 | Planning | Calculate permit fees | Determine all applicable fees | N | N | Y | Y | 95% | Fee Calculator | 10 | Per permit
T032 | Planning | Submit permit application | File with jurisdiction (online/in-person) | N | N | Y | Y | 70% | Permit Portal | 45 | Per permit
T033 | Planning | Track permit status daily | Monitor application progress | N | N | Y | Y | 95% | Permit Tracker | 10 | Daily
T034 | Planning | Respond to plan review comments | Address jurisdiction feedback | N | N | Y | Y | 40% | Comment Response | 120 | As needed
T035 | Planning | Coordinate design revisions | Manage revisions with designer | N | N | Y | Y | 60% | Revision Tracker | 60 | As needed
T036 | Planning | Notify client of permit status | Update client on approvals/issues | N | N | Y | Y | 100% | Client Notification | 5 | As needed
T037 | Planning | Download approved permits | Store permit documents | N | N | Y | Y | 95% | Document Vault | 5 | Per permit
T038 | Planning | Schedule initial inspections | Book required inspections | N | N | Y | Y | 85% | Inspection Scheduler | 15 | Per permit
T039 | Planning | Define bid requirements | Specify scope and qualifications | N | Y | Y | Y | 85% | Bid Engine | 30 | Per bid
T040 | Planning | Identify qualified contractors | Source 3+ qualified bidders | N | Y | Y | Y | 90% | Contractor Marketplace | 30 | Per bid
T041 | Planning | Issue bid invitations | Send RFP to contractors | N | Y | Y | Y | 95% | Bid Engine | 15 | Per bid
T042 | Planning | Conduct pre-bid site visit | Walk contractors through project | N | N | Y | Y | 0% | Calendar | 90 | Per bid
T043 | Planning | Collect bid submissions | Receive and organize bids | N | Y | Y | Y | 95% | Bid Collection Portal | 15 | Per bid
T044 | Planning | Analyze bids | Compare price, scope, timeline | N | Y | Y | Y | 85% | Bid Comparison Tool | 60 | Per bid
T045 | Planning | Verify contractor credentials | Check licenses, insurance, bonding | N | Y | Y | Y | 90% | Credential Verification | 20 | Per contractor
T046 | Planning | Present bid comparison | Create client-ready comparison | N | Y | Y | Y | 90% | Bid Report Generator | 30 | Per bid
T047 | Planning | Facilitate contractor interviews | Coordinate selection meetings | N | N | Y | Y | 70% | Video/Calendar | 60 | As needed
T048 | Planning | Document selection decision | Record rationale and approval | N | Y | Y | Y | 90% | Decision Log | 15 | Per bid
T049 | Planning | Generate contract | Create contract from approved bid | N | N | Y | Y | 90% | Contract Generator | 30 | Per contract
T050 | Planning | Include standard terms | Add scope, schedule, payment, warranty | N | N | Y | Y | 95% | Contract Templates | 15 | Per contract
T051 | Planning | Review contract with client | Walk through key terms | N | N | Y | Y | 20% | Video/Phone | 45 | Per contract
T052 | Planning | Coordinate modifications | Handle requested changes | N | N | Y | Y | 70% | Revision Tracker | 30 | As needed
T053 | Planning | Obtain client signature | Route for e-signature | N | N | Y | Y | 95% | DocuSign | 5 | Per contract
T054 | Planning | Obtain contractor signature | Route for e-signature | N | N | Y | Y | 95% | DocuSign | 5 | Per contract
T055 | Planning | Collect insurance certificates | Verify contractor insurance | N | N | Y | Y | 85% | Insurance Verification | 15 | Per contractor
T056 | Planning | Process initial payment | Collect deposit/mobilization | N | N | Y | Y | 95% | Stripe Escrow | 10 | Per contract
T057 | Planning | Issue Notice to Proceed | Authorize work to begin | N | N | Y | Y | 95% | NTP Generator | 5 | Per contract
T058 | Planning | Store executed contract | Archive in document vault | N | N | Y | Y | 100% | Document Vault | 2 | Per contract
T059 | Pre-Con | Receive contractor schedule | Get baseline schedule from GC | N | Y | Y | Y | 90% | Schedule Import | 15 | Per project
T060 | Pre-Con | Review schedule logic | Verify sequence and duration | N | Y | Y | Y | 60% | Schedule Review | 45 | Per project
T061 | Pre-Con | Verify milestone alignment | Match schedule to contract terms | N | Y | Y | Y | 90% | Milestone Mapper | 20 | Per project
T062 | Pre-Con | Identify critical path | Determine schedule-critical activities | N | Y | Y | Y | 85% | Critical Path Analysis | 30 | Per project
T063 | Pre-Con | Add inspection milestones | Insert inspection holds | N | N | Y | Y | 95% | Schedule Builder | 15 | Per project
T064 | Pre-Con | Coordinate material lead times | Track long-lead items | N | N | Y | Y | 80% | Lead Time Tracker | 45 | Per project
T065 | Pre-Con | Present schedule to client | Get schedule approval | N | Y | Y | Y | 70% | Schedule Presentation | 30 | Per project
T066 | Pre-Con | Baseline approved schedule | Lock baseline for variance tracking | N | Y | Y | Y | 95% | Schedule Lock | 5 | Per project
T067 | Pre-Con | Set up milestone reminders | Configure automated alerts | N | Y | Y | Y | 100% | Reminder Engine | 10 | Per project
T068 | Pre-Con | Publish schedule to stakeholders | Distribute to all parties | N | Y | Y | Y | 100% | Schedule Publish | 5 | Per project
T069 | Pre-Con | Compile material takeoff | List all required materials | N | N | Y | Y | 70% | Takeoff Tool | 90 | Per project
T070 | Pre-Con | Identify long-lead items | Flag items with extended lead times | N | N | Y | Y | 90% | Lead Time Database | 20 | Per project
T071 | Pre-Con | Coordinate material selections | Manage client selections | N | N | Y | Y | 50% | Selection Tracker | 120 | Per project
T072 | Pre-Con | Verify material availability | Check stock and pricing | N | N | Y | Y | 85% | Supplier Portal | 30 | Per project
T073 | Pre-Con | Create procurement schedule | Align deliveries with construction | N | N | Y | Y | 80% | Procurement Scheduler | 45 | Per project
T074 | Pre-Con | Place long-lead orders | Order critical items | N | N | N | Y | 85% | Order Management | 30 | Per project
T075 | Pre-Con | Confirm delivery logistics | Verify dates and access | N | N | Y | Y | 80% | Delivery Tracker | 20 | Per delivery
T076 | Pre-Con | Notify contractor of deliveries | Share delivery schedule | N | N | Y | Y | 95% | Contractor Portal | 5 | Per delivery
T077 | Construction | Review daily log | Analyze contractor's daily report | N | Y | Y | Y | 85% | Daily Log Portal | 15 | Daily
T078 | Construction | Compare progress to schedule | Track actual vs. baseline | N | Y | Y | Y | 90% | Schedule Variance | 10 | Daily
T079 | Construction | Review site photos | Analyze submitted progress photos | N | Y | Y | Y | 70% | Photo Review | 15 | Daily
T080 | Construction | Flag concerns | Document issues or deviations | N | Y | Y | Y | 80% | Issue Tracker | 10 | As needed
T081 | Construction | Update project dashboard | Refresh status indicators | N | Y | Y | Y | 95% | Dashboard | 5 | Daily
T082 | Construction | Respond to RFIs | Answer contractor questions | N | Y | Y | Y | 50% | RFI Manager | 30 | As needed
T083 | Construction | Coordinate owner decisions | Get client input when needed | N | Y | Y | Y | 60% | Decision Request | 20 | As needed
T084 | Construction | Document delays | Log weather/force majeure events | N | Y | Y | Y | 90% | Delay Log | 10 | As needed
T085 | Construction | Monitor site resources | Track labor and equipment | N | N | Y | Y | 75% | Resource Tracker | 10 | Daily
T086 | Construction | Update forecast | Revise projected completion | N | Y | Y | Y | 85% | Forecast Tool | 20 | Weekly
T087 | Construction | Schedule site visit | Book per package frequency | N | Y | Y | Y | 90% | Visit Scheduler | 10 | Per visit
T088 | Construction | Notify contractor | Inform of planned visit | N | Y | Y | Y | 100% | Notification Engine | 2 | Per visit
T089 | Construction | Prepare visit checklist | Generate phase-appropriate list | N | Y | Y | Y | 95% | Checklist Generator | 5 | Per visit
T090 | Construction | Conduct walkthrough | Physical inspection with contractor | N | Y | Y | Y | 0% | Mobile App | 90 | Per visit
T091 | Construction | Document progress photos | Take 10+ photos per visit | N | Y | Y | Y | 80% | Photo Documentation | 15 | Per visit
T092 | Construction | Note quality concerns | Document any issues found | N | Y | Y | Y | 70% | Issue Logger | 15 | Per visit
T093 | Construction | Verify against plans | Compare work to approved drawings | N | Y | Y | Y | 60% | Plan Comparison | 20 | Per visit
T094 | Construction | Complete visit report | Document all findings | N | Y | Y | Y | 90% | Report Generator | 30 | Per visit
T095 | Construction | Send report to client | Email summary with photos | N | Y | Y | Y | 100% | Email Engine | 5 | Per visit
T096 | Construction | Follow up on items | Track issue resolution | N | Y | Y | Y | 80% | Task Manager | 20 | Per visit
T097 | Construction | Map required inspections | List all inspections from permit | N | N | Y | Y | 95% | Inspection Matrix | 15 | Per project
T098 | Construction | Align to schedule | Map inspections to milestones | N | N | Y | Y | 90% | Schedule Integration | 10 | Per project
T099 | Construction | Request inspection | Schedule with jurisdiction | N | N | Y | Y | 85% | Inspection Request | 15 | Per inspection
T100 | Construction | Confirm inspection | Verify scheduling confirmation | N | N | Y | Y | 90% | Confirmation Tracker | 5 | Per inspection
T101 | Construction | Notify client | Inform of pending inspection | N | N | Y | Y | 100% | Client Notification | 2 | Per inspection
T102 | Construction | Verify site readiness | Ensure ready for inspector | N | N | Y | Y | 75% | Readiness Checklist | 15 | Per inspection
T103 | Construction | Document result | Record pass/fail and notes | N | N | Y | Y | 85% | Inspection Log | 10 | Per inspection
T104 | Construction | Coordinate corrections | Manage failed inspection items | N | N | Y | Y | 60% | Correction Tracker | 45 | As needed
T105 | Construction | Schedule re-inspection | Book follow-up inspection | N | N | Y | Y | 90% | Re-inspection Request | 10 | As needed
T106 | Construction | Update milestone | Mark milestone complete on pass | N | N | Y | Y | 95% | Milestone Tracker | 5 | Per inspection
T107 | Construction | Receive change request | Capture from client or contractor | N | N | Y | Y | 90% | Change Request Portal | 10 | As needed
T108 | Construction | Document scope change | Detail what is being changed | N | N | Y | Y | 70% | Change Description | 30 | Per CO
T109 | Construction | Request contractor pricing | Get cost from contractor | N | N | Y | Y | 95% | CO Pricing Request | 10 | Per CO
T110 | Construction | Review pricing | Evaluate reasonableness | N | N | Y | Y | 70% | Pricing Review | 30 | Per CO
T111 | Construction | Analyze schedule impact | Determine timeline effect | N | N | Y | Y | 80% | Schedule Impact Tool | 20 | Per CO
T112 | Construction | Prepare CO document | Generate formal change order | N | N | Y | Y | 90% | CO Generator | 20 | Per CO
T113 | Construction | Present to client | Explain change and impact | N | N | Y | Y | 40% | CO Presentation | 30 | Per CO
T114 | Construction | Obtain approval | Get client authorization | N | N | Y | Y | 90% | Approval Workflow | 10 | Per CO
T115 | Construction | Execute change order | Finalize approved change | N | N | Y | Y | 85% | CO Execution | 15 | Per CO
T116 | Construction | Update project records | Revise budget and schedule | N | N | Y | Y | 95% | Project Update | 10 | Per CO
T117 | Construction | Receive payment request | Get invoice from contractor | N | N | Y | Y | 95% | Payment Request Portal | 5 | Per milestone
T118 | Construction | Verify milestone completion | Confirm work is complete | N | N | Y | Y | 70% | Milestone Verification | 30 | Per payment
T119 | Construction | Review documentation | Check supporting materials | N | N | Y | Y | 80% | Document Review | 20 | Per payment
T120 | Construction | Conduct site verification | Physical inspection if needed | N | N | Y | Y | 0% | Site Verification | 60 | Per payment
T121 | Construction | Calculate payment | Determine amount per contract | N | N | Y | Y | 95% | Payment Calculator | 10 | Per payment
T122 | Construction | Apply retainage | Withhold per contract terms | N | N | Y | Y | 95% | Retainage Tracker | 5 | Per payment
T123 | Construction | Prepare recommendation | Create payment recommendation | N | N | Y | Y | 90% | Payment Report | 15 | Per payment
T124 | Construction | Send to client | Route for approval | N | N | Y | Y | 100% | Approval Workflow | 5 | Per payment
T125 | Construction | Process payment | Release funds upon approval | N | N | N | Y | 95% | Stripe Escrow | 5 | Per payment
T126 | Construction | Document payment | Record in project file | N | N | Y | Y | 100% | Payment Log | 5 | Per payment
T127 | Construction | Generate weekly report | Create detailed progress report | N | N | Y | Y | 95% | Report Generator | 45 | Weekly
T128 | Construction | Generate bi-weekly report | Create summary report | N | Y | N | N | 95% | Report Generator | 30 | Bi-weekly
T129 | Construction | Generate monthly report | Create comprehensive monthly | Y | N | N | N | 95% | Report Generator | 60 | Monthly
T130 | Construction | Conduct weekly call | Phone check-in with client | N | Y | Y | Y | 0% | Calendar + Phone | 30 | Weekly
T131 | Construction | Conduct monthly call | Monthly review with client | Y | N | N | N | 0% | Calendar + Phone | 30 | Monthly
T132 | Construction | Generate daily update | Brief daily summary | N | N | N | Y | 95% | Report Generator | 15 | Daily
T133 | Closeout | Schedule pre-final walkthrough | Book walkthrough 2 weeks before end | N | N | Y | Y | 90% | Calendar | 10 | Per project
T134 | Closeout | Conduct walkthrough | Physical inspection for punch list | N | N | Y | Y | 0% | Punch List App | 120 | Per project
T135 | Closeout | Document punch items | Photo and describe each item | N | N | Y | Y | 80% | Photo Documentation | 60 | Per project
T136 | Closeout | Assign responsibility | Designate who fixes each item | N | N | Y | Y | 70% | Punch List Manager | 20 | Per project
T137 | Closeout | Send to contractor | Distribute punch list | N | N | Y | Y | 100% | Contractor Portal | 5 | Per project
T138 | Closeout | Set completion deadline | Establish 2-week deadline | N | N | Y | Y | 95% | Deadline Tracker | 5 | Per project
T139 | Closeout | Track daily progress | Monitor item completion | N | N | Y | Y | 85% | Progress Tracker | 15 | Daily
T140 | Closeout | Conduct verification | Verify items are complete | N | N | Y | Y | 0% | Verification Visit | 60 | As needed
T141 | Closeout | Confirm all inspections passed | Verify all pass | N | N | Y | Y | 95% | Inspection Tracker | 10 | Per project
T142 | Closeout | Compile closeout documents | Gather all required docs | N | N | Y | Y | 85% | Document Compiler | 60 | Per project
T143 | Closeout | Schedule final inspection | Book with jurisdiction | N | N | Y | Y | 85% | Inspection Scheduler | 15 | Per project
T144 | Closeout | Verify site ready | Ensure ready for final | N | N | Y | Y | 75% | Readiness Checklist | 20 | Per project
T145 | Closeout | Attend final inspection | Be present at final | N | N | Y | Y | 0% | Calendar | 60 | Per project
T146 | Closeout | Document result | Record outcome | N | N | Y | Y | 85% | Inspection Log | 10 | Per project
T147 | Closeout | Obtain Certificate of Occupancy | Get CO from jurisdiction | N | N | Y | Y | 80% | Document Vault | 15 | Per project
T148 | Closeout | Send CO to client | Deliver certificate | N | N | Y | Y | 100% | Client Notification | 5 | Per project
T149 | Closeout | Compile documentation package | Assemble all project docs | N | N | Y | Y | 85% | Document Compiler | 90 | Per project
T150 | Closeout | Collect warranties | Gather all warranty documents | N | N | Y | Y | 70% | Warranty Tracker | 60 | Per project
T151 | Closeout | Gather manuals | Collect equipment manuals | N | N | Y | Y | 70% | Manual Collection | 45 | Per project
T152 | Closeout | Prepare final report | Create comprehensive final report | Y | Y | Y | Y | 90% | Report Generator | 60 | Per project
T153 | Closeout | Schedule handover meeting | Book final meeting with client | N | N | Y | Y | 90% | Calendar | 10 | Per project
T154 | Closeout | Conduct walkthrough with client | Final walk-through | N | N | Y | Y | 0% | Walkthrough | 60 | Per project
T155 | Closeout | Present documentation | Deliver full package to client | N | N | Y | Y | 70% | Document Delivery | 30 | Per project
T156 | Closeout | Explain warranty process | Educate on warranty claims | N | N | Y | Y | 50% | Warranty Education | 15 | Per project
T157 | Closeout | Process final payment | Release retainage | N | N | Y | Y | 95% | Stripe Escrow | 10 | Per project
T158 | Closeout | Send satisfaction survey | Request client feedback | Y | Y | Y | Y | 100% | Survey Engine | 5 | Per project
T159 | Closeout | Request referral | Ask for referrals/reviews | Y | Y | Y | Y | 80% | Referral Engine | 10 | Per project
T160 | Closeout | Archive project | Close and archive all records | Y | Y | Y | Y | 95% | Archive System | 15 | Per project

## App Requirements
App ID | App Name | Priority | Est. Weeks | Automation % | Key Features | Dependencies | API Integrations
APP-01 | Contractor Bid Engine | 1 (Build First) | 6-8 | 85% | Auto-matching, bid collection, comparison, credentials | Marketplace API | Stripe, License APIs
APP-02 | Site Visit Scheduler | 2 | 4-6 | 90% | Smart scheduling, route optimization, weather integration | Calendar, Maps | Google Calendar, Maps, Weather
APP-03 | Change Order Processor | 2 | 5-7 | 75% | Request intake, impact analysis, document generation | Contract data | DocuSign
APP-04 | Report Generator | 3 | 4-5 | 95% | All report types, photo integration, narrative AI | All project data | Claude API
APP-05 | Permit Tracker | 3 | 8-10 | 70% | Requirements engine, submission, status tracking | Jurisdiction portals | DC/MD/VA permit APIs
APP-06 | Inspection Coordinator | 3 | 6-8 | 75% | Scheduling, prep alerts, result tracking | Permit data | Jurisdiction systems
APP-07 | Budget Tracker | 3 | 5-7 | 85% | Cost tracking, variance analysis, forecasting | Financial data | Stripe, QuickBooks
APP-08 | Client Communication Hub | 3 | 4-6 | 80% | Templates, multi-channel, sentiment analysis | Client data | GoHighLevel, SendGrid, Twilio
APP-09 | Task Queue Manager | 1 (Build First) | 5-7 | 90% | Auto-generation, prioritization, assignment | All apps | Redis, BullMQ
APP-10 | Document Generator | 3 | 4-5 | 95% | Contracts, reports, permits, closeout packages | Templates | DocuSign
APP-11 | Predictive Issue Engine | 4 (AI) | 8-10 | N/A | Delay, cost, quality prediction | Historical data | ML models
APP-12 | Smart Scheduler | 4 (AI) | 6-8 | N/A | Optimization, resource leveling, recovery | Schedule data | Optimization algorithms
APP-13 | Automated QA Inspector | 4 (AI) | 10-12 | N/A | Photo analysis, defect detection, compliance | Photo data | Google Vision, TensorFlow
APP-14 | Decision Support AI | 4 (AI) | 8-10 | N/A | Recommendations, validation, benchmarking | All project data | Claude API, ML models

## Client Projections
Month | Pkg A Clients | Pkg A Revenue | Pkg B Clients | Pkg B Revenue | Pkg C Clients | Pkg C Revenue | Pkg D Clients | Pkg D Revenue | Total Clients | Total MRR | PM Hours/Wk | FTE Required
Month 1 | 20 | 35000 | 8 | 30000 | 5 | 47500 | 1 | 16500 | 34 | 129000 | 510 | 12.8
Month 2 | 20 | 35000 | 8 | 30000 | 5 | 47500 | 1 | 16500 | 34 | 129000 | 510 | 12.8
Month 3 | 20 | 35000 | 8 | 30000 | 5 | 47500 | 1 | 16500 | 34 | 129000 | 510 | 12.8
Month 4 | 25 | 43750 | 10 | 37500 | 6 | 57000 | 1 | 16500 | 42 | 154750 | 617 | 15.4
Month 5 | 25 | 43750 | 10 | 37500 | 6 | 57000 | 1 | 16500 | 42 | 154750 | 617 | 15.4
Month 6 | 25 | 43750 | 10 | 37500 | 6 | 57000 | 1 | 16500 | 42 | 154750 | 617 | 15.4
Month 7 | 31 | 54250 | 12 | 45000 | 7 | 66500 | 1 | 16500 | 51 | 182250 | 732 | 18.3
Month 8 | 31 | 54250 | 12 | 45000 | 7 | 66500 | 1 | 16500 | 51 | 182250 | 732 | 18.3
Month 9 | 31 | 54250 | 12 | 45000 | 7 | 66500 | 1 | 16500 | 51 | 182250 | 732 | 18.3
Month 10 | 39 | 68250 | 15 | 56250 | 9 | 85500 | 1 | 16500 | 64 | 226500 | 915 | 22.9
Month 11 | 39 | 68250 | 15 | 56250 | 9 | 85500 | 1 | 16500 | 64 | 226500 | 915 | 22.9
Month 12 | 39 | 68250 | 15 | 56250 | 9 | 85500 | 1 | 16500 | 64 | 226500 | 915 | 22.9

## Implementation Roadmap
Week | Phase | Focus Area | Deliverables | Apps Built | Milestone
1-2 | Phase 1: Foundation | Infrastructure | Redis, BullMQ, Temporal.io, base integrations | Infrastructure | Backend ready
2-3 | Phase 1: Foundation | Priority Apps | Contractor Bid Engine v1 | APP-01 | Bid automation live
3-4 | Phase 1: Foundation | Priority Apps | Task Queue Manager v1 | APP-09 | Work queue active
5-6 | Phase 2: Field Ops | Site Operations | Site Visit Scheduler | APP-02 | Visits automated
6-7 | Phase 2: Field Ops | Mobile | Mobile field app v1 | Mobile App | Field-ready
7-8 | Phase 2: Field Ops | Change Mgmt | Change Order Processor | APP-03 | CO workflow live
9-10 | Phase 3: Communications | Reporting | Report Generator | APP-04 | Auto-reports live
10-11 | Phase 3: Communications | Client Comms | Client Communication Hub | APP-08 | Client portal live
11-12 | Phase 3: Communications | Documents | Document Generator | APP-10 | Docs automated
13-15 | Phase 4: Permits | Permits | Permit Tracker | APP-05 | Permit tracking live
15-17 | Phase 4: Permits | Inspections | Inspection Coordinator | APP-06 | Inspections automated
17-18 | Phase 4: Permits | Budget | Budget Tracker | APP-07 | Financials live
19-20 | Phase 5: AI | Predictions | Predictive Issue Engine | APP-11 | Issue prediction live
20-22 | Phase 5: AI | Optimization | Smart Scheduler | APP-12 | Schedule AI live
22-24 | Phase 5: AI | Decisions | Decision Support AI | APP-14 | AI recommendations live
25-28 | Phase 6: Advanced | Computer Vision | Automated QA Inspector | APP-13 | Photo AI live
28-30 | Phase 6: Advanced | Integration | Full integration + optimization | All | PLATFORM COMPLETE