## App Staffing Matrix
App ID | App Name | Complexity | Build Team | Build Weeks | Maint. FTE | Ops FTE | Skills Required | Can Combine With
APP-01 | Contractor Bid Engine | High | 2 devs | 6-8 | 0.15 | 0.1 | Full-stack, ML basics, API integrations | APP-09
APP-02 | Site Visit Scheduler | Medium | 1 dev | 4-6 | 0.08 | 0.05 | Full-stack, Google APIs, Mobile | APP-06
APP-03 | Change Order Processor | Medium | 1 dev | 5-7 | 0.08 | 0.08 | Full-stack, DocuSign, Workflows | APP-10
APP-04 | Report Generator | Medium | 1 dev | 4-5 | 0.1 | 0.05 | Full-stack, AI/LLM, PDF generation | APP-10
APP-05 | Permit Tracker | High | 2 devs | 8-10 | 0.15 | 0.15 | Full-stack, Web scraping, Jurisdiction APIs | APP-06
APP-06 | Inspection Coordinator | Medium | 1 dev | 6-8 | 0.1 | 0.1 | Full-stack, Calendar, Notifications | APP-05
APP-07 | Budget Tracker | Medium | 1 dev | 5-7 | 0.1 | 0.08 | Full-stack, Financial, Stripe | APP-03
APP-08 | Communication Hub | Medium | 1 dev | 4-6 | 0.08 | 0.05 | Full-stack, GoHighLevel, Twilio, SendGrid | APP-04
APP-09 | Task Queue Manager | High | 2 devs | 5-7 | 0.12 | 0.08 | Full-stack, Redis, BullMQ, Temporal | APP-01
APP-10 | Document Generator | Low | 1 dev | 4-5 | 0.05 | 0.03 | Full-stack, DocuSign, Templates | APP-03, APP-04
APP-11 | Predictive Issue Engine | Very High | 1 ML + 1 dev | 8-10 | 0.2 | 0.05 | ML/AI, TensorFlow, Data science | APP-14
APP-12 | Smart Scheduler | High | 1 ML + 1 dev | 6-8 | 0.15 | 0.05 | ML/AI, Optimization algorithms | APP-02
APP-13 | Automated QA Inspector | Very High | 1 ML + 1 dev | 10-12 | 0.25 | 0.05 | Computer Vision, TensorFlow, Google Vision | APP-11
APP-14 | Decision Support AI | High | 1 ML + 1 dev | 8-10 | 0.15 | 0.05 | ML/AI, Claude API, Data modeling | APP-11
TOTALS

## Role Definitions
Role | Responsibilities | Skills Required | Salary Range | Apps Covered
Senior Full-Stack Dev | Build & maintain core apps, API development, integrations, code reviews | Next.js, Fastify, Prisma, TypeScript, Redis, 5+ yrs exp | $120K-$160K | APP-01 to APP-10
ML/AI Engineer | Build & maintain AI apps, train models, optimize predictions | Python, TensorFlow, scikit-learn, Claude API, 3+ yrs ML exp | $140K-$180K | APP-11 to APP-14
Junior Full-Stack Dev | Support development, testing, documentation, bug fixes | Next.js, TypeScript, 1-3 yrs exp | $70K-$95K | Support all apps
DevOps Engineer | Infrastructure, CI/CD, monitoring, scaling, security | Railway, Vercel, Docker, Redis, monitoring tools | $110K-$150K | All apps infrastructure
QA Engineer | Testing, automation, quality assurance, bug tracking | Jest, Playwright, API testing, 2+ yrs exp | $80K-$110K | All apps
Technical PM | Coordinate development, sprint planning, stakeholder communication | Agile, JIRA, technical background, 3+ yrs exp | $100K-$130K | All apps coordination

## Staffing by Phase
Phase | Duration | Senior Dev | ML Engineer | Junior Dev | DevOps | QA | Tech PM | Total FTE | Monthly Cost
Phase 1: Foundation | Weeks 1-4 | 2 | 0 | 1 | 0.5 | 0.5 | 0.5 | 4.5 | $52,500
Phase 2: Field Ops | Weeks 5-8 | 1.5 | 0 | 1 | 0.25 | 0.5 | 0.5 | 3.75 | $41,250
Phase 3: Communications | Weeks 9-12 | 1.5 | 0.5 | 1 | 0.25 | 0.5 | 0.5 | 4.25 | $51,875
Phase 4: Permits | Weeks 13-18 | 2 | 0 | 1 | 0.25 | 0.5 | 0.5 | 4.25 | $47,500
Phase 5: AI Layer | Weeks 19-24 | 1 | 2 | 0.5 | 0.25 | 0.5 | 0.5 | 4.75 | $62,500
Phase 6: Advanced AI | Weeks 25-30 | 0.5 | 2 | 0.5 | 0.25 | 0.5 | 0.25 | 4 | $55,000
--- | --- | --- | --- | --- | --- | --- | --- | --- | ---
ONGOING MAINTENANCE | Monthly | 0.5 | 0.3 | 0.2 | 0.1 | 0.2 | 0.2 | 1.5 | $17,500
ONGOING OPERATIONS | Monthly | 0 | 0 | 0.2 | 0.1 | 0 | 0.1 | 0.4 | $4,500

## Recommended Teams
TEAM STRUCTURE OPTIONS
OPTION A: MINIMUM VIABLE (Startup Mode)
Role | Count | Cost/Month | Coverage
Senior Full-Stack Developer | 1 | $12,500 | All 14 apps (stretched thin)
ML/AI Engineer (Part-time/Contract) | 0.5 | $7,500 | AI apps only when needed
Founder/Technical PM | 0.25 | $0 (equity) | Coordination
TOTAL | 1.75 FTE | $20,000/mo | High risk, slow velocity
OPTION B: BALANCED (Recommended)
Role | Count | Cost/Month | Coverage
Senior Full-Stack Developer | 2 | $25,000 | Core apps (APP-01 to APP-10)
ML/AI Engineer | 1 | $15,000 | AI apps (APP-11 to APP-14)
Junior Developer | 1 | $7,500 | Support, testing, docs
DevOps (Part-time) | 0.25 | $3,000 | Infrastructure
Technical PM (Part-time) | 0.5 | $5,500 | Coordination
TOTAL | 4.75 FTE | $56,000/mo | Good velocity, manageable risk
OPTION C: ACCELERATED (Fast Track)
Role | Count | Cost/Month | Coverage
Senior Full-Stack Developer | 3 | $37,500 | Parallel development tracks
ML/AI Engineer | 2 | $30,000 | AI apps + research
Junior Developer | 2 | $15,000 | Support, testing, docs
DevOps Engineer | 0.5 | $6,000 | Infrastructure, monitoring
QA Engineer | 1 | $8,000 | Dedicated testing
Technical PM | 1 | $11,000 | Full-time coordination
TOTAL | 9.5 FTE | $107,500/mo | Fast delivery, low risk

## Ongoing Operations
POST-LAUNCH STAFFING REQUIREMENTS
Once all 14 apps are built and deployed:
Function | FTE | Monthly Cost | Responsibilities
MAINTENANCE
Bug fixes & patches | 0.3 | $3,750 | Fix issues, security patches, dependency updates
Feature enhancements | 0.4 | $5,000 | Minor improvements, user feedback implementation
AI model retraining | 0.3 | $4,500 | Update prediction models, improve accuracy
Integration updates | 0.2 | $2,500 | API changes, third-party updates
Maintenance Subtotal | 1.2 FTE | $15,750
OPERATIONS
Monitoring & alerts | 0.1 | $1,200 | System health, performance monitoring
Data management | 0.1 | $1,200 | Backups, data quality, cleanup
User support (L2) | 0.2 | $2,500 | Technical support escalations
Infrastructure | 0.1 | $1,200 | Scaling, optimization, cost management
Operations Subtotal | 0.5 FTE | $6,100
TOTAL ONGOING | 1.7 FTE | $21,850/mo | Post-launch steady state

## Cost Summary
TOTAL COST OF OWNERSHIP - 24 MONTH VIEW
Category | Duration | FTE | Total Cost
BUILD PHASE (Option B)
Phase 1: Foundation | 4 weeks | 4.5 | $52,500
Phase 2: Field Ops | 4 weeks | 3.75 | $41,250
Phase 3: Communications | 4 weeks | 4.25 | $51,875
Phase 4: Permits | 6 weeks | 4.25 | $71,250
Phase 5: AI Layer | 6 weeks | 4.75 | $93,750
Phase 6: Advanced AI | 6 weeks | 4.0 | $82,500
Build Subtotal | 30 weeks | Avg 4.25 | $393,125
ONGOING (Months 8-24)
Maintenance | 17 months | 1.2 | $267,750
Operations | 17 months | 0.5 | $103,700
Ongoing Subtotal | 17 months | 1.7 | $371,450
24-MONTH TOTAL |  |  | $764,575
COMPARISON
Without automation (25 PMs @ $65K) | 24 months | 25 | $3,250,000
With automation (10 PMs + tech) | 24 months | 10 + 1.7 | $2,364,575
NET SAVINGS | 24 months |  | $885,425