KEALEE PLATFORM v10

PM MODULE EXECUTION FRAMEWORK

Complete SOP, SOW, Task Matrix & Automation Architecture

Prepared for: Kealee Construction LLC

Document Version: 1.0

Date: January 25, 2026

# 1. EXECUTIVE SUMMARY

This document provides the complete execution framework for the Kealee PM Module (os-pm), including industry-standard construction management SOPs, platform-specific workflows, scope of work templates, task matrices, and automation architecture specifications.

## 1.1 Business Projections

Based on your provided growth targets with 25% monthly scaling after Month 3:

| Period | Pkg A ($1,750) | Pkg B ($3,750) | Pkg C ($9,500) | Pkg D ($16,500) | Total Clients | Monthly MRR |
| --- | --- | --- | --- | --- | --- | --- |
| Month 1-3 | 20 | 8 | 5 | 1 | 34 | $129,000 |
| Month 4-6 | 25 | 10 | 6 | 1 | 42 | $161,250 |
| Month 7-9 | 31 | 13 | 8 | 2 | 54 | $214,250 |
| Month 10-12 | 39 | 16 | 10 | 2 | 67 | $272,500 |

## 1.2 PM Staffing Requirements

Hours required per week based on package tier commitments:

| Package | Hrs/Week | Month 1-3 Load | Month 10-12 Load |
| --- | --- | --- | --- |
| Package A (5-10 hrs/wk avg) | 7.5 | 150 hrs | 293 hrs |
| Package B (15-20 hrs/wk avg) | 17.5 | 140 hrs | 280 hrs |
| Package C (30-40 hrs/wk avg) | 35 | 175 hrs | 350 hrs |
| Package D (40+ hrs/wk avg) | 45 | 45 hrs | 90 hrs |
| TOTAL | - | 510 hrs/wk | 1,013 hrs/wk |
| FTE Required (40 hr/wk) | - | 13 PMs | 25 PMs |

With AI automation targeting 60% efficiency gains, actual PM requirement reduces to 5-6 PMs for Month 1-3 and 10-12 PMs for Month 10-12.

# 2. INDUSTRY STANDARD CONSTRUCTION MANAGEMENT SOP

The following Standard Operating Procedures follow industry best practices from PMI, CMAA, and AIA guidelines adapted for residential and light commercial construction management.

## 2.1 Project Lifecycle Phases

| Phase | Duration | Key Activities | Deliverables |
| --- | --- | --- | --- |
| 1. Initiation | Week 1 | Client intake, needs assessment, site visit | Project brief, initial estimate |
| 2. Planning | Weeks 2-4 | Design, engineering, permits, contractor selection | Plans, permits, contracts |
| 3. Pre-Construction | Weeks 4-6 | Mobilization, scheduling, materials | Schedule, material orders |
| 4. Construction | Weeks 6-24+ | Execution, monitoring, inspections | Progress reports, approvals |
| 5. Closeout | Final 2 wks | Final inspection, punch list, handover | Certificate of occupancy |

## 2.2 Phase 1: Project Initiation SOP

### SOP-001: Client Intake Process

Purpose: Capture complete project requirements and client expectations within 48 hours of inquiry.

Trigger: New lead from marketplace, referral, or direct inquiry

Owner: Assigned PM

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 1.1 | Receive notification of new client assignment | Immediate | os-pm Queue |
| 1.2 | Review client submission (project type, budget, timeline) | 15 min | m-ops-services data |
| 1.3 | Conduct initial phone consultation (30-60 min) | Within 24 hrs | Calendar + Call Script |
| 1.4 | Complete Client Intake Form with all project details | During call | Intake Form Generator |
| 1.5 | Upload photos/documents from client | Within 24 hrs | Document Vault |
| 1.6 | Classify project type and complexity | 15 min | AI Classification Engine |
| 1.7 | Generate initial budget estimate range | Auto | Estimation Engine |
| 1.8 | Send intake confirmation email with next steps | Immediate | Email Template Engine |
| 1.9 | Schedule discovery site visit (if Package C/D) | Within 48 hrs | Calendar Sync |
| 1.10 | Create project record in system | Auto | API/Database |

### SOP-002: Site Assessment Process

Purpose: Document existing conditions and validate project feasibility.

Trigger: Project requires in-person assessment (Package C/D or complex projects)

Owner: PM or designated assessor

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 2.1 | Confirm appointment with client 24 hours in advance | Day before | SMS/Email Automation |
| 2.2 | Review project brief and prepare assessment checklist | 30 min | Checklist Generator |
| 2.3 | Conduct on-site measurements and documentation | 1-2 hours | Mobile App + Camera |
| 2.4 | Photograph all relevant areas (min 20 photos) | During visit | Photo Documentation |
| 2.5 | Complete site assessment form | During visit | Mobile Assessment Form |
| 2.6 | Identify potential issues, code concerns, access challenges | During visit | Issue Tracker |
| 2.7 | Discuss timeline expectations with client | During visit | Verbal |
| 2.8 | Upload all documentation to project file | Within 2 hrs | Document Vault |
| 2.9 | Generate site assessment report | Same day | Report Generator |
| 2.10 | Send summary to client with findings | Within 24 hrs | Email Engine |

### SOP-003: Project Classification

Purpose: Categorize projects for proper resource allocation and workflow routing.

Classification Matrix:

| Classification | Budget Range | Duration | Permits Required | Example Projects |
| --- | --- | --- | --- | --- |
| Simple | $5K-$25K | 1-4 weeks | None/Minor | Paint, flooring, fixtures |
| Standard | $25K-$100K | 4-12 weeks | Standard | Kitchen/bath remodel |
| Complex | $100K-$500K | 12-24 weeks | Multiple | Additions, full renovations |
| Major | $500K+ | 24+ weeks | Extensive | New construction, gut rehab |

## 2.3 Phase 2: Planning SOP

### SOP-004: Design Coordination

Purpose: Manage design development from concept through construction documents.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 4.1 | Determine design requirements based on scope | Day 1 | Scope Analysis |
| 4.2 | Match with appropriate design professional | Day 1-2 | Architect Marketplace |
| 4.3 | Facilitate design kickoff meeting | Day 3-5 | Calendar + Video |
| 4.4 | Review conceptual designs with client (2-3 options) | Week 2 | Design Review Tool |
| 4.5 | Document client selections and preferences | Week 2 | Decision Log |
| 4.6 | Coordinate design development drawings | Weeks 2-3 | Design Tracking |
| 4.7 | Review drawings for code compliance | Week 3 | Compliance Checker |
| 4.8 | Coordinate engineering if required (structural, MEP) | Weeks 3-4 | Engineer Network |
| 4.9 | Facilitate client approval of final design | Week 4 | Approval Workflow |
| 4.10 | Obtain construction documents for permitting | Week 4 | Document Vault |

### SOP-005: Permit Management

Purpose: Navigate permit requirements and obtain all required approvals.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 5.1 | Identify required permits by jurisdiction | Day 1 | Permit Requirements DB |
| 5.2 | Compile permit application package | Days 2-3 | Permit Package Builder |
| 5.3 | Calculate permit fees | Auto | Fee Calculator API |
| 5.4 | Submit permit application (online or in-person) | Day 3-4 | Permit Portal Integration |
| 5.5 | Track application status daily | Ongoing | Permit Tracker |
| 5.6 | Respond to plan review comments within 48 hours | As needed | Comment Response Tool |
| 5.7 | Coordinate revisions with design team | As needed | Revision Tracker |
| 5.8 | Notify client of approval/issues | Same day | Client Notification |
| 5.9 | Download and store approved permits | Upon approval | Document Vault |
| 5.10 | Schedule required inspections | Day of approval | Inspection Scheduler |

### SOP-006: Contractor Selection

Purpose: Source and qualify contractors through competitive bidding.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 6.1 | Define scope and bid requirements | Day 1 | Bid Package Builder |
| 6.2 | Identify qualified contractors (min 3) | Day 1-2 | Contractor Marketplace |
| 6.3 | Issue bid invitations with deadline | Day 2 | Bid Invitation Engine |
| 6.4 | Conduct pre-bid site visit if needed | Day 3-5 | Calendar |
| 6.5 | Collect and organize bid submissions | Deadline + 1 | Bid Collection Portal |
| 6.6 | Analyze bids (price, scope, timeline) | Day 1-2 | Bid Comparison Tool |
| 6.7 | Verify contractor credentials | Day 2-3 | Credential Verification |
| 6.8 | Present bid comparison to client | Day 3 | Bid Report Generator |
| 6.9 | Facilitate contractor interviews if requested | Days 4-5 | Video/Calendar |
| 6.10 | Document client selection and rationale | Day 5-6 | Decision Log |

### SOP-007: Contract Administration

Purpose: Execute binding agreements between parties.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 7.1 | Generate contract from approved bid | Day 1 | Contract Generator |
| 7.2 | Include scope, schedule, payment terms, warranties | Day 1 | Contract Templates |
| 7.3 | Review contract with client | Day 2 | Contract Review |
| 7.4 | Coordinate contract modifications if needed | Days 2-3 | Revision Tracker |
| 7.5 | Obtain client signature | Day 3-4 | E-Signature (DocuSign) |
| 7.6 | Obtain contractor signature | Day 4-5 | E-Signature |
| 7.7 | Collect insurance certificates | Day 5 | Insurance Verification |
| 7.8 | Process initial payment/deposit | Day 5-6 | Stripe Escrow |
| 7.9 | Issue Notice to Proceed | Day 6 | NTP Generator |
| 7.10 | Store executed contract in document vault | Same day | Document Vault |

## 2.4 Phase 3: Pre-Construction SOP

### SOP-008: Project Scheduling

Purpose: Create detailed project schedule with milestones and dependencies.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 8.1 | Receive contractor baseline schedule | Week 1 | Schedule Import |
| 8.2 | Review schedule logic and duration | Day 1-2 | Schedule Review Tool |
| 8.3 | Verify milestone alignment with contract | Day 2 | Milestone Mapper |
| 8.4 | Identify critical path activities | Day 2 | Critical Path Analysis |
| 8.5 | Add inspection and approval milestones | Day 3 | Schedule Builder |
| 8.6 | Coordinate material lead times | Day 3-4 | Lead Time Tracker |
| 8.7 | Present schedule to client for approval | Day 5 | Schedule Presentation |
| 8.8 | Baseline approved schedule | Day 5 | Schedule Lock |
| 8.9 | Set up automated milestone reminders | Day 5 | Reminder Engine |
| 8.10 | Publish schedule to all stakeholders | Day 5 | Schedule Publish |

### SOP-009: Material Procurement Coordination

Purpose: Ensure timely delivery of materials to prevent schedule delays.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 9.1 | Compile material takeoff from plans | Week 1 | Takeoff Tool |
| 9.2 | Identify long-lead items (windows, cabinets, etc.) | Day 1 | Lead Time Database |
| 9.3 | Coordinate material selections with client | Week 1-2 | Selection Tracker |
| 9.4 | Verify material availability and pricing | Day 2-3 | Supplier Portal |
| 9.5 | Create procurement schedule aligned with construction | Day 3 | Procurement Scheduler |
| 9.6 | Place orders for long-lead items | Day 4-5 | Order Management |
| 9.7 | Confirm delivery dates and logistics | Day 5 | Delivery Tracker |
| 9.8 | Notify contractor of expected deliveries | Ongoing | Contractor Portal |
| 9.9 | Track shipments and resolve delivery issues | Ongoing | Shipment Tracker |
| 9.10 | Document material receipts and condition | Upon delivery | Receipt Documentation |

## 2.5 Phase 4: Construction Management SOP

### SOP-010: Daily Monitoring

Purpose: Maintain visibility into project progress and identify issues early.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 10.1 | Review contractor daily log/report | Each morning | Daily Log Portal |
| 10.2 | Compare progress to schedule | Daily | Schedule Variance Tool |
| 10.3 | Review site photos submitted by contractor | Daily | Photo Review |
| 10.4 | Flag any concerns or deviations | Immediate | Issue Tracker |
| 10.5 | Update project dashboard status | Daily | Dashboard |
| 10.6 | Respond to contractor RFIs within 24 hours | As needed | RFI Manager |
| 10.7 | Coordinate any required owner decisions | As needed | Decision Request |
| 10.8 | Document weather delays or force majeure | As occurs | Delay Log |
| 10.9 | Monitor labor and equipment on site | Daily | Resource Tracker |
| 10.10 | Update forecast based on actual progress | Weekly | Forecast Tool |

### SOP-011: Site Visit Protocol

Purpose: Conduct regular site inspections to verify quality and progress.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 11.1 | Schedule site visit based on package (1-4x/month) | Weekly | Visit Scheduler |
| 11.2 | Notify contractor of planned visit | 24 hrs prior | Notification Engine |
| 11.3 | Prepare site visit checklist | Day before | Checklist Generator |
| 11.4 | Conduct walkthrough with contractor | On site | Mobile Checklist |
| 11.5 | Document progress photos (min 10 per visit) | On site | Photo Documentation |
| 11.6 | Note any quality concerns or code issues | On site | Issue Logger |
| 11.7 | Verify work matches approved plans | On site | Plan Comparison |
| 11.8 | Complete site visit report | Same day | Report Generator |
| 11.9 | Send report to client | Within 24 hrs | Email Engine |
| 11.10 | Follow up on any open items from visit | Within 48 hrs | Task Manager |

### SOP-012: Inspection Coordination

Purpose: Schedule and manage required inspections with jurisdiction.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 12.1 | Identify all required inspections from permit | Project start | Inspection Matrix |
| 12.2 | Map inspections to project schedule | Day 1 | Schedule Integration |
| 12.3 | Contractor requests inspection (72 hrs notice) | Per schedule | Inspection Request |
| 12.4 | Confirm inspection scheduled with jurisdiction | Same day | Confirmation Tracker |
| 12.5 | Notify client of pending inspection | 24 hrs prior | Client Notification |
| 12.6 | Ensure site is ready for inspection | Day before | Readiness Checklist |
| 12.7 | Document inspection result | Same day | Inspection Log |
| 12.8 | If failed, coordinate corrections with contractor | Within 24 hrs | Correction Tracker |
| 12.9 | Schedule re-inspection if needed | Same day | Re-inspection Request |
| 12.10 | Update milestone status upon passing | Immediate | Milestone Tracker |

### SOP-013: Change Order Management

Purpose: Process scope changes with proper documentation and approval.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 13.1 | Receive change request (client or contractor) | Day 0 | Change Request Portal |
| 13.2 | Document scope change in detail | Day 1 | Change Description |
| 13.3 | Request contractor pricing for change | Day 1 | CO Pricing Request |
| 13.4 | Review contractor pricing within 48 hours | Days 2-3 | Pricing Review |
| 13.5 | Analyze schedule impact | Day 3 | Schedule Impact Tool |
| 13.6 | Prepare change order document | Day 4 | CO Generator |
| 13.7 | Present to client with recommendation | Day 4-5 | CO Presentation |
| 13.8 | Obtain client approval/rejection | Days 5-7 | Approval Workflow |
| 13.9 | Execute change order if approved | Day 7 | CO Execution |
| 13.10 | Update budget, schedule, and contract | Same day | Project Update |

### SOP-014: Progress Payments

Purpose: Process milestone-based payments accurately and timely.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 14.1 | Receive payment request from contractor | Per milestone | Payment Request Portal |
| 14.2 | Verify milestone completion | Day 1 | Milestone Verification |
| 14.3 | Review supporting documentation | Day 1 | Document Review |
| 14.4 | Conduct site verification if required | Day 1-2 | Site Verification |
| 14.5 | Calculate payment amount per contract | Day 2 | Payment Calculator |
| 14.6 | Apply any retainage per contract terms | Day 2 | Retainage Tracker |
| 14.7 | Prepare payment recommendation | Day 2 | Payment Report |
| 14.8 | Send to client for approval | Day 2 | Approval Workflow |
| 14.9 | Process payment upon approval | Day 3 | Stripe Escrow Release |
| 14.10 | Document payment in project records | Same day | Payment Log |

## 2.6 Phase 5: Project Closeout SOP

### SOP-015: Punch List Management

Purpose: Document and track completion of all outstanding items.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 15.1 | Schedule pre-final walkthrough with contractor | 2 wks before end | Calendar |
| 15.2 | Conduct walkthrough and document items | Scheduled day | Punch List App |
| 15.3 | Photograph each punch list item | During walkthrough | Photo Documentation |
| 15.4 | Assign priority and responsible party | Same day | Punch List Manager |
| 15.5 | Send punch list to contractor | Same day | Contractor Portal |
| 15.6 | Set completion deadline (typically 2 weeks) | Same day | Deadline Tracker |
| 15.7 | Track daily progress on items | Daily | Progress Tracker |
| 15.8 | Conduct verification walkthrough | Upon completion | Verification Visit |
| 15.9 | Close items or add new items found | Same day | Punch List Update |
| 15.10 | Repeat until all items complete | As needed | Iteration Tracker |

### SOP-016: Final Inspection

Purpose: Obtain final approval from jurisdiction.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 16.1 | Confirm all required inspections passed | Day 1 | Inspection Tracker |
| 16.2 | Verify punch list 100% complete | Day 1 | Punch List Status |
| 16.3 | Compile close-out documents | Day 1-2 | Document Compiler |
| 16.4 | Schedule final inspection with jurisdiction | Day 2 | Inspection Scheduler |
| 16.5 | Ensure site is final-inspection ready | Day before | Readiness Checklist |
| 16.6 | Attend final inspection | Scheduled day | Calendar |
| 16.7 | Document result | Same day | Inspection Log |
| 16.8 | If issues, coordinate corrections | Immediate | Correction Tracker |
| 16.9 | Obtain Certificate of Occupancy | Upon approval | Document Vault |
| 16.10 | Send CO to client | Same day | Client Notification |

### SOP-017: Project Handover

Purpose: Transfer project to owner with all documentation.

Steps:

| Step | Action | Timeline | Tool/System |
| --- | --- | --- | --- |
| 17.1 | Compile project documentation package | Final week | Document Compiler |
| 17.2 | Collect all warranties from contractors | Final week | Warranty Tracker |
| 17.3 | Gather equipment manuals and specs | Final week | Manual Collection |
| 17.4 | Prepare final project report | Final week | Report Generator |
| 17.5 | Schedule handover meeting with client | Final week | Calendar |
| 17.6 | Walk through completed project with client | Handover day | Walkthrough |
| 17.7 | Present documentation package | Handover day | Document Delivery |
| 17.8 | Explain warranty process | Handover day | Warranty Education |
| 17.9 | Process final payment/retainage release | Upon acceptance | Stripe Escrow |
| 17.10 | Send project completion survey | Day after | Survey Engine |

# 3. PACKAGE-SPECIFIC SCOPE OF WORK TEMPLATES

The following SOW templates define deliverables by package tier. Each template should be customized for specific project requirements.

## 3.1 Package A - Basic Support ($1,750/month)

Service Commitment: 5-10 hours per week of PM support

Target Client: Budget-conscious homeowners managing contractors directly who need oversight and guidance.

### Package A Deliverables:

| Deliverable | Frequency | Description |
| --- | --- | --- |
| Monthly Check-in Call | 1x/month (30 min) | Review project status, address questions, provide guidance |
| Quarterly Progress Report | 1x/quarter | Written summary of project status, budget, and timeline |
| Email Support | 48-hour response | Answers to project questions and contractor concerns |
| Document Review | As requested | Review contracts, bids, or plans with written feedback |
| Vendor Recommendations | As needed | Referrals to qualified contractors in our network |
| Budget Tracking | Monthly update | Track expenses vs. initial budget estimate |

### Package A Exclusions:

Site visits, permit management, inspection coordination, contractor hiring, direct contractor communication, daily monitoring, change order processing, payment administration.

## 3.2 Package B - Professional ($3,750/month)

Service Commitment: 15-20 hours per week of PM support

Target Client: Homeowners who want regular oversight and contractor coordination but handle day-to-day decisions.

### Package B Deliverables:

| Deliverable | Frequency | Description |
| --- | --- | --- |
| Weekly Check-in Call | 1x/week (30 min) | Detailed project review, upcoming week planning |
| Bi-Weekly Progress Report | 2x/month | Written report with photos, schedule, and budget status |
| Priority Support | 24-hour response | Phone and email support for urgent matters |
| Contractor Coordination | Ongoing | Direct communication with contractors on your behalf |
| Budget Tracking | Weekly update | Detailed expense tracking and variance analysis |
| Schedule Monitoring | Weekly | Track progress against baseline schedule |
| Site Visits | 2x/month | In-person site inspections with written report |
| RFI Management | As needed | Coordinate contractor questions and owner decisions |

### Package B Exclusions:

Permit application/tracking, inspection scheduling, contractor hiring (recommendations only), design coordination, change order processing (documentation only), payment administration.

## 3.3 Package C - Premium ($9,500/month)

Service Commitment: 30-40 hours per week of dedicated PM support

Target Client: Homeowners who want comprehensive project management with minimal personal involvement.

### Package C Deliverables:

| Deliverable | Frequency | Description |
| --- | --- | --- |
| Daily Project Monitoring | Every business day | Review progress, photos, and contractor reports |
| Weekly Detailed Report | 1x/week | Comprehensive report with photos, budget, schedule, risks |
| Dedicated PM Access | Business hours | Direct phone and email with same-day response |
| Site Visits | 4x/month | Weekly inspections with quality control checklist |
| Complete Permit Management | Full service | Application, tracking, revisions, approval |
| Inspection Coordination | Full service | Schedule, prepare, attend, document all inspections |
| Contractor Management | Full oversight | Daily communication, issue resolution, performance |
| Budget Management | Real-time | Track all costs, approve invoices, manage cash flow |
| Schedule Management | Real-time | Monitor progress, identify delays, coordinate recovery |
| Change Order Processing | Full service | Document, price, present, execute all changes |
| Quality Control | Per visit | Systematic quality inspections against standards |
| Risk Management | Ongoing | Identify, assess, and mitigate project risks |
| 0% Marketplace Fee | All transactions | No platform fee on contractor hires via marketplace |

### Package C Exclusions:

Contractor hiring (PM recommends, client decides), design services (coordination only), direct payments to contractors (client processes).

## 3.4 Package D - Enterprise ($16,500/month)

Service Commitment: 40+ hours per week of full-service turnkey management

Target Client: High-end clients who want complete white-glove service with zero personal involvement in project details.

### Package D Deliverables (Everything in Package C plus):

| Deliverable | Frequency | Description |
| --- | --- | --- |
| Full Contractor Procurement | As needed | Source, vet, select, and contract all contractors |
| Design Coordination | Full service | Manage designer/architect throughout project |
| Payment Administration | Full service | Review invoices, recommend payment, process escrow |
| Daily Progress Updates | Every day | Brief daily summary to client (email or text) |
| 24/7 Emergency Access | Always | Direct PM line for urgent matters any time |
| Owner Representation | All meetings | Represent owner at all contractor meetings |
| Warranty Management | Full lifecycle | Track warranties, coordinate warranty claims |
| Project Closeout | Full service | Complete documentation package, handover, final report |
| Dedicated Account Manager | Assigned | Single point of contact for all project matters |
| Custom Reporting | As requested | Tailored reports for investor, partner, or personal needs |
| Multi-Project Coordination | If applicable | Portfolio view across multiple simultaneous projects |
| Strategic Advisory | Ongoing | Guidance on major decisions, vendor selection, value engineering |

### Package D Full Authority:

PM has authority to make decisions up to $5,000 without owner approval (customizable). All decisions documented and communicated same-day.

# 4. MASTER TASK LIST BY PACKAGE TIER

Complete inventory of all tasks required to execute PM services, organized by package tier and phase.

## 4.1 Package A Tasks (63 total)

| Phase | Task Count | Key Tasks |
| --- | --- | --- |
| Initiation | 8 | Intake form, initial call, budget estimate, project setup |
| Planning | 12 | Review plans, document feedback, vendor referrals, timeline review |
| Construction | 35 | Monthly calls, email support, document review, budget tracking |
| Closeout | 8 | Final report, satisfaction survey, referral request |

## 4.2 Package B Tasks (142 total)

| Phase | Task Count | Key Tasks |
| --- | --- | --- |
| Initiation | 15 | Intake, site visit, classification, contractor recommendations |
| Planning | 28 | Design review, permit guidance, bid review, schedule setup |
| Construction | 85 | Weekly calls, site visits, contractor coordination, reporting |
| Closeout | 14 | Final walkthrough, documentation, survey, referral |

## 4.3 Package C Tasks (247 total)

| Phase | Task Count | Key Tasks |
| --- | --- | --- |
| Initiation | 22 | Full intake, site assessment, classification, project setup |
| Planning | 58 | Design coordination, permit application, contractor selection |
| Construction | 145 | Daily monitoring, weekly visits, inspections, change orders |
| Closeout | 22 | Punch list, final inspection, documentation, handover |

## 4.4 Package D Tasks (312 total)

| Phase | Task Count | Key Tasks |
| --- | --- | --- |
| Initiation | 28 | VIP intake, comprehensive assessment, strategy development |
| Planning | 72 | Full design management, permit execution, contractor hiring |
| Construction | 180 | Daily updates, on-site representation, full administration |
| Closeout | 32 | Complete closeout, warranty setup, final presentation |

# 5. AUTOMATION APP ARCHITECTURE

Based on your requirements for internal PM automation and AI-driven intelligent systems, the following 14 micro-applications are required to achieve target efficiency gains.

## 5.1 Priority 1: Build First (Your Ranking: 3)

### App 1: Contractor Bid Engine

Purpose: Automate contractor sourcing, bid collection, and comparison

Automation Level: 85% automated, 15% PM review

| Feature | Description | AI Component |
| --- | --- | --- |
| Auto-matching | Match project to qualified contractors based on trade, location, history | ML matching algorithm |
| Bid invitation | Generate and send bid packages automatically | Template + NLP customization |
| Bid collection | Portal for contractors to submit structured bids | Form parsing + validation |
| Comparison engine | Analyze bids across 12 criteria (price, time, qualifications) | Weighted scoring AI |
| Recommendation | Generate client-ready bid comparison with recommendation | Decision support AI |
| Credential verification | Auto-verify licenses, insurance, bonding | API integrations + validation |

Integration: m-marketplace, Stripe, credential APIs

Est. Development: 6-8 weeks

## 5.2 Priority 2: Build Second (Your Ranking: 4)

### App 2: Site Visit Scheduler

Purpose: Intelligent scheduling of site visits with route optimization

Automation Level: 90% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Smart scheduling | Auto-schedule visits based on package tier and project phase | Rule engine + calendar AI |
| Route optimization | Optimize visit order for multi-site days | Google Maps API + optimizer |
| Checklist generation | Create phase-appropriate checklist before each visit | Template AI |
| Weather integration | Reschedule outdoor work assessments for weather | Weather API + scheduler |
| Notification system | Auto-notify contractor and client of visit | Multi-channel notifications |
| Mobile app | Field-ready mobile interface for PM during visits | React Native app |

Integration: Google Calendar, Google Maps, Weather API, Push notifications

Est. Development: 4-6 weeks

### App 3: Change Order Processor

Purpose: Streamline change order workflow from request to execution

Automation Level: 75% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Request intake | Capture change requests from multiple sources | Form + email parsing |
| Impact analysis | Auto-calculate schedule and budget impact | Project modeling AI |
| Pricing request | Auto-request pricing from contractor | Template + tracking |
| Document generation | Generate change order document from approved request | Document AI |
| Approval workflow | Route for client approval with e-signature | Workflow engine + DocuSign |
| Project update | Auto-update budget, schedule, and records | Integration layer |

Integration: DocuSign, project database, Stripe

Est. Development: 5-7 weeks

## 5.3 Priority 3: Build Third (Your Ranking: 5)

### App 4: Report Generator

Purpose: Auto-generate all client reports based on project data

Automation Level: 95% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Template library | Pre-built templates for each report type | Configurable templates |
| Data aggregation | Pull data from all project sources | ETL pipeline |
| Photo integration | Auto-insert recent site photos with captions | Image selection AI |
| Narrative generation | Generate written narrative from data points | GPT-4 integration |
| Schedule to send | Auto-generate and send per package schedule | Cron + email engine |
| Client portal | Publish reports to client portal automatically | Portal integration |

Report Types: Daily update, weekly detailed, bi-weekly summary, monthly, quarterly, final

Integration: All project data sources, email, client portal

Est. Development: 4-5 weeks

### App 5: Permit Tracker

Purpose: Track permit applications through jurisdictions with automated status updates

Automation Level: 70% automated (limited by jurisdiction APIs)

| Feature | Description | AI Component |
| --- | --- | --- |
| Requirements engine | Determine required permits by jurisdiction and project type | Rules database + AI |
| Package builder | Compile permit application package from project docs | Document assembly |
| Submission tracking | Track submission status with jurisdiction portals | Web scraping + API |
| Comment response | Alert PM to plan review comments, suggest responses | NLP comment analysis |
| Fee calculation | Auto-calculate permit fees by jurisdiction | Fee database + calculator |
| Timeline prediction | Predict approval timeline based on historical data | ML prediction model |

Jurisdictions (Phase 1): DC DCRA, Montgomery County DPS, Prince George's DPIE, Fairfax County LDS

Integration: Jurisdiction portals (where available), document vault

Est. Development: 8-10 weeks

### App 6: Inspection Coordinator

Purpose: Schedule and track all required inspections

Automation Level: 75% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Inspection matrix | Map required inspections from permit to schedule | Rules engine |
| Readiness checker | Verify site ready for inspection based on checklist | Checklist AI |
| Scheduling | Request inspection with jurisdiction (IVR or portal) | Integration layer |
| Preparation alerts | Notify contractor of prep requirements | Notification engine |
| Result tracking | Log inspection results and corrections needed | Form + tracker |
| Re-inspection | Auto-schedule re-inspection upon correction | Workflow engine |

Integration: Jurisdiction inspection systems, calendar, contractor portal

Est. Development: 6-8 weeks

### App 7: Budget Tracker

Purpose: Real-time project financial tracking and variance analysis

Automation Level: 85% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Cost tracking | Track all project costs against budget line items | Categorization AI |
| Invoice processing | Receive, validate, and route invoices for approval | OCR + validation |
| Variance analysis | Calculate and alert on budget variances | Threshold engine |
| Forecast modeling | Project final cost based on current trajectory | ML forecasting |
| Cash flow | Track payments and project cash flow | Financial modeling |
| Reporting | Generate financial reports for client | Report generator |

Integration: Stripe, QuickBooks (optional), project database

Est. Development: 5-7 weeks

### App 8: Client Communication Hub

Purpose: Centralize and automate client communication

Automation Level: 80% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Template library | Pre-built templates for all standard communications | Template engine |
| Smart compose | AI-assisted message composition from bullet points | GPT-4 integration |
| Multi-channel | Send via email, SMS, or portal based on preference | Channel router |
| Auto-updates | Send automated updates at scheduled intervals | Scheduler |
| Response tracking | Track client response and follow up if needed | Follow-up engine |
| Sentiment analysis | Analyze client communications for satisfaction | NLP sentiment AI |

Integration: GoHighLevel, SendGrid, Twilio, client portal

Est. Development: 4-6 weeks

### App 9: Task Queue Manager

Purpose: Intelligent work queue management for PMs

Automation Level: 90% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Task generation | Auto-generate tasks from SOP triggers | Event-driven tasks |
| Prioritization | AI-prioritize tasks by urgency and impact | Priority scoring AI |
| Assignment | Auto-assign to PM based on workload | Load balancing |
| Deadline tracking | Track deadlines and escalate overdue | Deadline engine |
| Dependency management | Track task dependencies and sequences | DAG processor |
| Performance analytics | Track PM productivity and task completion | Analytics engine |

Integration: All other apps (trigger tasks), PM dashboard

Est. Development: 5-7 weeks

### App 10: Document Generator

Purpose: Generate all project documents from templates and data

Automation Level: 95% automated

| Feature | Description | AI Component |
| --- | --- | --- |
| Contract generation | Generate contracts from templates + project data | Document assembly |
| Report generation | Create formatted reports (PDF, DOCX) | Template engine |
| Permit packages | Compile permit application packages | Package builder |
| Closeout packages | Generate warranty and handover packages | Package builder |
| E-signature | Route documents for signature | DocuSign integration |
| Version control | Track document versions and changes | Version manager |

Document Types: Contracts, change orders, reports, permits, punch lists, closeout packages

Integration: DocuSign, document vault, all data sources

Est. Development: 4-5 weeks

## 5.4 AI Intelligence Layer

Four AI-powered systems that make autonomous decisions and predictions:

### App 11: Predictive Issue Engine

Purpose: Predict project issues before they occur

| Capability | Description | Training Data |
| --- | --- | --- |
| Delay prediction | Predict schedule delays from early signals | Historical project data |
| Budget overrun | Predict cost overruns from spending patterns | Financial history |
| Quality issues | Flag potential quality concerns from inspection patterns | Inspection data |
| Contractor risk | Assess contractor performance risk | Contractor history |
| Weather impact | Predict weather-related delays | Weather + project data |
| Intervention timing | Recommend when PM should intervene | Outcome data |

Output: Risk scores, alerts, recommended actions

Est. Development: 8-10 weeks

### App 12: Smart Scheduler

Purpose: Optimize project schedules and resource allocation

| Capability | Description | Algorithm |
| --- | --- | --- |
| Schedule optimization | Optimize task sequences for critical path | CPM + ML |
| Resource leveling | Balance PM workload across projects | Constraint optimization |
| Conflict resolution | Identify and resolve scheduling conflicts | Conflict detection AI |
| Recovery planning | Generate recovery plans for delays | Scenario modeling |
| Lead time management | Track and optimize material lead times | Supply chain AI |

Est. Development: 6-8 weeks

### App 13: Automated QA Inspector

Purpose: AI-powered quality assurance from photos and reports

| Capability | Description | Technology |
| --- | --- | --- |
| Photo analysis | Analyze site photos for progress and quality | Computer vision |
| Progress estimation | Estimate % complete from visual inspection | Object detection + ML |
| Defect detection | Identify potential defects in photos | Anomaly detection |
| Code compliance | Flag potential code violations from images | Rules + CV |
| Report generation | Generate QA reports from analysis | NLG |

Est. Development: 10-12 weeks

### App 14: Decision Support AI

Purpose: Assist PMs with complex decisions

| Capability | Description | Approach |
| --- | --- | --- |
| Bid analysis | Recommend contractor selection from bid analysis | Multi-criteria scoring |
| Change evaluation | Assess change order reasonableness | Pricing database + ML |
| Risk assessment | Evaluate project risk factors | Risk scoring model |
| Timeline estimation | Estimate realistic project timelines | Historical analysis |
| Cost estimation | Validate contractor pricing against benchmarks | Cost database + ML |

Est. Development: 8-10 weeks

# 6. TECHNOLOGY STACK REQUIREMENTS

## 6.1 Core Platform (Existing)

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js 14 (App Router) | All PM-facing interfaces |
| Backend API | Fastify | API gateway and business logic |
| Database | Supabase (PostgreSQL) | Primary data store |
| ORM | Prisma | Database access layer |
| Payments | Stripe | Billing and escrow |
| Hosting | Vercel (FE) / Railway (API) | Deployment infrastructure |
| Auth | Supabase Auth | Authentication and authorization |

## 6.2 Automation Layer (New)

| Component | Technology | Purpose |
| --- | --- | --- |
| Job Queue | BullMQ + Redis | Background job processing |
| Workflow Engine | Temporal.io | Complex workflow orchestration |
| Scheduling | node-cron + agenda | Scheduled task execution |
| Event Bus | Redis Pub/Sub | Real-time event distribution |
| Caching | Redis | Performance caching layer |

## 6.3 AI/ML Layer (New)

| Component | Technology | Purpose |
| --- | --- | --- |
| LLM | Claude API (Anthropic) | Natural language generation, analysis |
| Computer Vision | Google Cloud Vision | Photo analysis, defect detection |
| ML Models | Python + scikit-learn | Prediction models, scoring |
| Vector DB | Pinecone or pgvector | Semantic search, embeddings |
| Training Pipeline | MLflow | Model training and versioning |

## 6.4 Integration Layer

| Integration | Technology/API | Purpose |
| --- | --- | --- |
| E-Signature | DocuSign API | Contract and approval signatures |
| Calendar | Google Calendar API | Scheduling and availability |
| Maps/Routes | Google Maps Platform | Route optimization, location |
| Weather | OpenWeather API | Weather-based scheduling |
| Email | SendGrid | Transactional email |
| SMS | Twilio | SMS notifications |
| CRM | GoHighLevel API | Lead and client management |
| Permits (DC) | DCRA Portal (scraping) | Permit status tracking |
| Permits (MD) | County portals (scraping) | Permit status tracking |

## 6.5 Mobile (Field Operations)

| Component | Technology | Purpose |
| --- | --- | --- |
| Mobile Framework | React Native | Cross-platform mobile app |
| Offline Support | WatermelonDB | Offline-first data |
| Camera | Native camera + compression | Site photo capture |
| Location | Expo Location | GPS for site visits |

# 7. IMPLEMENTATION ROADMAP

Phased rollout over 24 weeks, prioritized by your ranking and business impact.

## 7.1 Phase 1: Foundation (Weeks 1-4)

Focus: Core infrastructure and highest-priority automation

| Week | Deliverable | Apps/Components |
| --- | --- | --- |
| 1-2 | Infrastructure setup | Redis, BullMQ, Temporal.io, base integrations |
| 2-3 | Contractor Bid Engine v1 | App 1: Matching, bid collection, comparison |
| 3-4 | Task Queue Manager v1 | App 9: Task generation, prioritization, assignment |

Milestone: PMs can use bid engine to automate contractor selection process

## 7.2 Phase 2: Scheduling & Visits (Weeks 5-8)

Focus: Field operations automation

| Week | Deliverable | Apps/Components |
| --- | --- | --- |
| 5-6 | Site Visit Scheduler | App 2: Smart scheduling, route optimization |
| 6-7 | Mobile field app v1 | Photo capture, checklist, offline support |
| 7-8 | Change Order Processor | App 3: Request to execution workflow |

Milestone: Field operations fully supported with mobile app and automated scheduling

## 7.3 Phase 3: Communications & Reporting (Weeks 9-12)

Focus: Client experience automation

| Week | Deliverable | Apps/Components |
| --- | --- | --- |
| 9-10 | Report Generator | App 4: All report types auto-generated |
| 10-11 | Client Communication Hub | App 8: Templates, multi-channel, automation |
| 11-12 | Document Generator | App 10: Contracts, permits, closeout packages |

Milestone: All client communications and reports automated

## 7.4 Phase 4: Permits & Inspections (Weeks 13-18)

Focus: Jurisdiction integration

| Week | Deliverable | Apps/Components |
| --- | --- | --- |
| 13-15 | Permit Tracker | App 5: Requirements, submission, tracking |
| 15-17 | Inspection Coordinator | App 6: Scheduling, prep, tracking |
| 17-18 | Budget Tracker | App 7: Cost tracking, variance, forecasting |

Milestone: Full permit and inspection lifecycle automated

## 7.5 Phase 5: AI Intelligence (Weeks 19-24)

Focus: Predictive and decision-support AI

| Week | Deliverable | Apps/Components |
| --- | --- | --- |
| 19-20 | Predictive Issue Engine | App 11: Delay, cost, quality prediction |
| 20-22 | Smart Scheduler | App 12: Optimization, resource leveling |
| 22-24 | Decision Support AI | App 14: Recommendations, validation |

Milestone: Full AI-powered construction management platform

## 7.6 Phase 6: Advanced AI (Weeks 25-30)

Focus: Computer vision and advanced automation

| Week | Deliverable | Apps/Components |
| --- | --- | --- |
| 25-28 | Automated QA Inspector | App 13: Photo analysis, defect detection |
| 28-30 | Integration refinement | All apps fully integrated and optimized |

Milestone: Industry-leading AI-powered PM platform

# 8. EXECUTIVE SUMMARY

## 8.1 Total Automation Apps: 14

| Priority | App Count | Est. Weeks | Automation Impact |
| --- | --- | --- | --- |
| Priority 1 (Build First) | 1 app | 6-8 weeks | Contractor selection 85% automated |
| Priority 2 (Build Second) | 2 apps | 9-13 weeks | Field ops 80% automated |
| Priority 3 (Build Third) | 7 apps | 35-45 weeks | Core PM tasks 85% automated |
| Priority 4 (AI Layer) | 4 apps | 32-40 weeks | Decision making 70% AI-assisted |
| TOTAL | 14 apps | 24-30 weeks* | Overall 60% efficiency gain |

*Parallelized development with 2-3 person team

## 8.2 Resource Requirements

| Resource | Quantity | Duration | Est. Cost |
| --- | --- | --- | --- |
| Senior Full-Stack Developer | 2 | 30 weeks | $90,000-$120,000 |
| ML/AI Engineer | 1 | 20 weeks | $50,000-$70,000 |
| UI/UX Designer | 1 (part-time) | 10 weeks | $15,000-$25,000 |
| DevOps/Infrastructure | 1 (part-time) | 8 weeks | $12,000-$20,000 |
| Third-party APIs/Services | - | Annual | $15,000-$25,000/year |
| TOTAL (Development) | - | 30 weeks | $182,000-$260,000 |

## 8.3 ROI Projection

With 60% efficiency gains from automation:

| Metric | Before Automation | After Automation | Savings |
| --- | --- | --- | --- |
| PMs needed (Month 1-3) | 13 FTE | 5-6 FTE | $280,000/year |
| PMs needed (Month 12) | 25 FTE | 10-12 FTE | $520,000/year |
| Tasks automated | 0% | 60% | - |
| Report generation time | 4 hrs/report | 15 min/report | 94% reduction |
| Bid collection time | 8 hrs/project | 1 hr/project | 87% reduction |

Payback Period: 4-6 months after full deployment

This document provides the complete framework for executing the Kealee PM module. All SOPs follow industry standards and are customized for your package tiers. The automation architecture is designed to scale with your projected growth while maintaining service quality.

END OF DOCUMENT